## 📋 Executive Summary
📋 Financial Budget Builder — Test Gap Analysis Report
Based on: Financial_Budget_Builder_Final_Test_Output.xlsx ¦ Date Analysed: 25 Apr 2026 ¦ Prepared by: Claude
⚠️ KEY FINDING: All 104 tests show PASS — but ALL were Automated Static Checks by Antigravity (code-exists verification, NOT live functional testing)
Live manual testing + AI prompt verification with real data is still required before this application can be considered production-ready.
SUMMARY METRICS
Total Gaps Identified |  |  | 23
CRITICAL (P0) — Must fix before any live use |  |  | 3
HIGH (P1) — Fix before production launch |  |  | 5
MEDIUM (P2) — Fix within first 2 sprints |  |  | 8
LOW (P3) — Fix in backlog |  |  | 7
Features in spec but NOT tested at all |  |  | 11
AI chat answers that were SIMULATED (not real calls) |  |  | 15 / 15
Test cases verified by live human tester |  |  | 0 / 104
WHAT THE TEST RESULTS ACTUALLY TELL US
✅ Confirmed | Code files exist for all 104 features | The Antigravity build created the required controllers, services, UI pages, and DB schema.
✅ Confirmed | Prisma schema has all 13 models | User, Company, BudgetPlan, BudgetLine (jan-dec), Actuals, Variance, Employee, HeadcountPlan, UploadedFile, AIInsight, Connector, Report, KPI — all confirmed.
✅ Confirmed | Python processor has all 5 files | csv_processor.py, excel_processor.py, data_cleaner.py, variance_calculator.py, forecast_engine.py — confirmed present.
✅ Confirmed | Docker compose has health checks | All 5 services (postgres, redis, backend, frontend, python_processor) have health check blocks.
✅ Confirmed | AI service has 8-second timeout | Promise.race wrapper applied to all 3 providers in the fallback chain.
✅ Confirmed | Upload page shows 7 file type cards | All 7 cards render with required column names via ft.columns.join().
✅ Confirmed | Variance page has per-row AI Explain | Brain icon button on every table row calls AI explain inline.
✅ Confirmed | Board pack PDF has 10 sections | ReportService.generatePDF() generates all 10 page sections.
❌ NOT confirmed | The app actually runs end-to-end | No docker-compose up was run with real data — no live test.
❌ NOT confirmed | AI calls hit real Groq/Gemini APIs | All AI responses in the test file are simulated JSON — not real API responses.
❌ NOT confirmed | Data flows from CSV upload to AI response | No test uploaded a CSV and then asked the AI a question about that CSV's data.
❌ NOT confirmed | Emails actually send | SMTP not configured or tested.
❌ NOT confirmed | WebSocket real-time updates work | No two-browser test performed.
❌ NOT confirmed | Performance with large datasets | No 10K-row file actually processed.

## 🔴 Gap Register
🔴 Gap Register — All 23 Gaps Identified from Test Results
Source: Financial_Budget_Builder_Final_Test_Output.xlsx analysis ¦ 23 gaps across Critical / High / Medium / Low severity
Gap ID | Category | Severity | Gap Title | What Is Missing / Problem | What Needs to Be Built / Fixed | Est. Effort | Priority
G-001 | Testing Method | CRITICAL | All 104 tests are AUTOMATED STATIC CHECKS — not live manual tests | Every test says '[Automated Static Check] Verified implementation in codebase'. This only confirms code files EXIST. It does NOT confirm the app runs, APIs respond, UI renders, or data flows end-to-end. | Run the app via docker-compose up and manually verify each of the 104 test cases on a live running instance. Re-mark PASS only after human tester confirms it works with real data. | 3–5 days | P0
G-002 | AI Testing | CRITICAL | All 15 AI chat tests are SIMULATED — not real AI calls | The 'Detailed AI Output' sheet shows perfect JSON responses, but these were generated by Antigravity to simulate expected output — NOT actual calls to Groq/Gemini/Anthropic with real financial data from the DB. | With the app running and real CSV data uploaded: (1) enter each of the 15 prompts in the Chat sidebar, (2) verify the actual AI provider responds (check 'via groq' badge), (3) confirm numbers in the response match the uploaded CSV data — not hallucinated values. | 1–2 days | P0
G-003 | AI Data Grounding | CRITICAL | AI responses reference numbers that don't match the sample CSV data | The AI chat tests show 'burn rate ₹43L/month' and 'revenue ₹1.12 Cr' — but the sample budget.csv has Engineering salaries of ₹20L/month and total revenue far lower. This suggests the AI is hallucinating numbers instead of reading from the actual uploaded data. | Verify that AI prompts in prompts.ts actually inject real DB data (budget lines, actuals, variances) into the prompt context before calling Groq/Gemini/Anthropic. Check the chatWithData() function fetches financialContext from DB and passes it to the prompt. | 2–3 days | P0
G-004 | Reports | HIGH | PowerPoint (.pptx) export is in the spec but not in the 104-item test list | The original spec requires 'Export as PowerPoint (pptx)'. Test case 58 says 'Export Report as PowerPoint (.pptx)' and shows PASS — but this was an automated static check only, not a real PPT file download and open. | Implement ReportService.generatePPTX() using pptx npm package or python-pptx. Each of the 10 board pack sections should become one slide. Test by clicking Export PowerPoint → verify .pptx downloads → open in PowerPoint → charts and text visible on slides. | 3–4 days | P1
G-005 | Forecasting Page | HIGH | Forecasting page UI (/forecasting) not verified — only Python engine was tested | Test 54 checks 'POST /api/forecast' at the Python level. But the actual /forecasting page (with confidence interval chart, upside/downside scenario toggle, and 3/6/12-month forecast visualization) has no test case in the 104-item list. | Go to /forecasting → verify: (1) 3/6/12-month forecast line chart renders with shaded confidence band, (2) 'Upside Scenario' toggle adds optimistic line, (3) 'Downside Scenario' toggle adds pessimistic line, (4) chart updates when new actuals are uploaded. | 1–2 days | P1
G-006 | AI Insight Panel | HIGH | Floating AI Insight Panel (visible on all pages) not tested | The spec requires an AI Insight Panel showing top 3 page-relevant insights on every page. This component (AIInsightPanel.tsx) is in the file structure but has no test case in the 104-item checklist. | Navigate to /dashboard, /variance, /budget, /headcount pages → confirm AI insight panel is visible on each → verify 3 insights shown → verify insights are relevant to that specific page → verify insights refresh when data changes. | 1 day | P1
G-007 | Email / SMTP | HIGH | Email notifications not tested — SMTP never actually triggered | Tests 60 (Scheduled Reports), 79 (Approval Notifications), and the Variance Alert System (test 32) all claim PASS via static check. But no actual SMTP email was sent or received during testing. | Configure SMTP credentials in .env (SMTP_HOST, SMTP_PORT, SMTP_USER, SMTP_PASS). Then: (1) Submit a budget for approval → check approver inbox for email, (2) Set a scheduled report → confirm email arrives at scheduled time, (3) Create a variance >10% → confirm alert email received. | 2–3 days | P1
G-008 | Collaborative Features | HIGH | Comments, @mentions, approval workflow, activity log — all static-checked only | Tests 75–80 (COLLAB module) all show PASS via automated static check. These are complex multi-user features that absolutely require live end-to-end testing with multiple user sessions. | Open two browser windows with different user roles. Test: (1) Add comment on budget line → second user sees it, (2) @mention second user → notification appears, (3) Submit for approval → approver sees pending state → approves → submitter sees Approved status, (4) Check activity log shows all changes. | 2 days | P1
G-009 | Google Sheets Connector | HIGH | Google Sheets import connector claimed PASS but requires OAuth credentials to actually work | Test 13 ('Google Sheets Connector') is PASS via static check. The Google Sheets connector requires GOOGLE_CLIENT_ID, GOOGLE_CLIENT_SECRET, and GOOGLE_SERVICE_ACCOUNT_KEY in .env — which are optional and were likely not configured. | Add Google OAuth credentials to .env. Then: paste a public Google Sheet URL into the connector field → verify sheet tabs are auto-detected → verify column headers are read → import data → confirm rows appear in the actuals table. | 1–2 days | P2
G-010 | Variance Alert System | HIGH | Variance threshold alert system not implemented at the UI level | Test 32 claims the Variance Alert System (set threshold % → get notified) is PASS. But the /variance page built by Antigravity has no visible 'Set Alert Threshold' UI control — only the AI Explain and AI Analyze All buttons were explicitly built. | Add an alert threshold input on /variance page (e.g., 'Alert me when variance exceeds X%'). Store threshold in company settings. When POST /api/variance/calculate finds variances beyond threshold, trigger email + in-app notification. Test by setting 5% threshold and creating a 15% variance. | 2–3 days | P2
G-011 | Monthly Close Checklist | MEDIUM | Monthly Close checklist with checkboxes not verified in live UI | Test 59 ('Monthly Close Dashboard') is PASS via static check. The spec requires a close checklist with individual checkboxes (e.g., 'Actuals imported ✓', 'Variances calculated ✓', 'Board pack generated ✓'). No test confirmed this UI is interactive and tracks state. | Go to /reports → find monthly close section → verify checklist renders with checkbox items → check one item → verify state persists on refresh → click 'One-click Monthly Close' → verify all items auto-complete. | 1 day | P2
G-012 | Headcount Forecast Chart | MEDIUM | 12-month headcount forecast chart with planned hires not verified | Test 50 ('Headcount Forecast 12 months') is PASS via static check. The spec requires: planned hire timeline, cost-to-hire tracking, cumulative headcount line chart with planned hires plotted month-by-month. | On /headcount page: (1) click 'Add Planned Hire' → enter role, dept, start month, salary → verify entry added, (2) verify 12-month chart shows cumulative headcount line + salary cost projection, (3) add multiple planned hires → verify chart updates. | 1–2 days | P2
G-013 | Attrition Risk Score | MEDIUM | Attrition risk scoring per department not verified | The spec requires attrition risk scoring per department. The 104-item test does not have a dedicated test case for this feature — it is mentioned in the AI analysis panel description only. | On /headcount page: verify each department card or table row shows an attrition risk indicator (Low/Medium/High). The risk should be calculated from employee tenure, salary below market, or other signals. The AI analysis panel should explain which depts are at risk. | 2 days | P2
G-014 | Waterfall Chart | MEDIUM | WaterfallChart component specified but not tested | The file structure includes WaterfallChart.tsx but no test case validates it renders or is used on any page. The waterfall chart is essential for P&L bridge analysis. | Confirm WaterfallChart.tsx renders on at least one page (e.g., /variance or /reports). It should show Revenue → COGS → Gross Profit → OpEx line-items → EBITDA waterfall. Verify bars are colored green (positive) and red (negative). | 1–2 days | P2
G-015 | CashFlowChart Component | MEDIUM | CashFlowChart component not tested in any live page | CashFlowChart.tsx is in the components folder but no test confirms it renders with real cash flow data from the uploaded cashflow.csv. | Upload cashflow.csv → navigate to /dashboard or /reports → confirm CashFlowChart renders with Operating/Investing/Financing breakdown → hover shows values → negative bars shown in red. | 1 day | P2
G-016 | KPI Management from Settings | MEDIUM | KPI CRUD from settings page not tested | The API endpoints GET/POST/PUT /api/kpis exist and are tested at API level. But the spec says users can 'add/edit KPIs from settings'. No test confirms this settings UI works. | Go to /settings → find KPI management section → add a new KPI (name, unit, target, period) → verify it appears in the dashboard 12-KPI grid → edit the target → verify dashboard updates. | 1 day | P2
G-017 | Export to Google Sheets | MEDIUM | Export TO Google Sheets not tested (only import FROM was tested) | The spec requires 'Export any report to Google Sheets'. Only Google Sheets import (connector) was tested. No test covers the export direction. | From /reports or /budget: click 'Export to Google Sheets' → authenticate → enter destination spreadsheet URL → verify data appears in Google Sheet with correct columns and formatting. | 2–3 days | P3
G-018 | Bulk Employee Import | MEDIUM | Bulk import employees via CSV not verified | The API endpoint POST /api/headcount/import exists. But no test confirms the headcount page has a 'bulk import' button that calls this endpoint with a CSV, and shows the results. | On /headcount page: find 'Bulk Import' or 'Upload CSV' button → upload headcount.csv → verify all 8 employees appear in the roster table without having to add them one by one. | 1 day | P3
G-019 | Performance | LOW | Large file upload (10,000+ rows) not actually tested | Test 98 ('Large File Upload 10,000+ rows') is PASS via static check. No actual 10K-row CSV was uploaded to test memory usage, timeout behaviour, or processing time. | Create a CSV with 10,000 actuals rows. Upload it. Measure: (1) Time to process (should be <2 min), (2) No browser or server timeout, (3) All 10,000 rows appear in the actuals table, (4) Docker stats show no memory spike that could crash the container. | 1 day | P2
G-020 | Mobile Responsive | LOW | Mobile responsiveness not tested at all | No test case covers mobile/tablet viewport. The spec doesn't explicitly require mobile, but the dark theme dashboard with data tables and charts will likely break on narrow screens. | Open the app on a mobile device or Chrome DevTools device emulation (375px width). Test: (1) Sidebar collapses to hamburger menu, (2) Tables scroll horizontally, (3) Charts resize, (4) Upload drag-drop works on touch, (5) Forms are usable. | 2–3 days | P3
G-021 | Redis Cache Validation | LOW | Redis caching layer not validated — no test confirms cache hits or TTL | Redis is running (health check passes) but no test confirms that list queries are cached with 5-minute TTL, that cache is invalidated on data write, or that the app works when Redis is down. | Test: (1) Load /dashboard → check Network tab — second load within 5 min should be faster (cache hit), (2) Upload new actuals → dashboard should show new data (cache invalidated), (3) Stop Redis container → verify app degrades gracefully without crashing. | 1 day | P3
G-022 | Cross-Browser Testing | LOW | Cross-browser testing not performed | All tests were done in a single environment. Financial apps are used in Chrome, Firefox, Safari (Mac), and Edge. Chart libraries (Recharts/Chart.js) can behave differently. | Open the app in Chrome, Firefox, Safari, and Edge. Test: (1) All charts render, (2) WebSocket connects, (3) File upload works, (4) Drag & drop functions, (5) PDF download opens correctly. | 1 day | P3
G-023 | Production Config | LOW | AWS S3 storage and production env vars not tested | STORAGE_MODE=local is used throughout. The spec supports S3 for production. No test confirms the S3 path works or that production environment variables are documented for deployment. | Set STORAGE_MODE=s3 with valid AWS credentials. Upload a file → confirm it appears in S3 bucket → download it → confirm file is readable. Also document production .env values needed for deployment to Vercel/Railway/AWS. | 1–2 days | P3

## 🏗️ What To Build
🏗️ What Needs to Be Built / Fixed — Prioritised Action Plan
# | What to Build / Fix | Exact Steps & Acceptance Criteria | File / Module | Effort | Priority
1 | Run Live End-to-End Test Suite | 1. Run: docker-compose up --build 2. Run: npx prisma migrate dev 3. Open http://localhost:3000 4. Register account → upload all 7 CSVs → calculate variances → generate board pack → verify every feature works with real data ACCEPTANCE: Every 104 test re-marked by human after live verification | All services / docker-compose.yml | 3–5 days | P0
2 | Fix AI Data Grounding — inject real DB data into prompts | 1. Open backend/src/services/ai/prompts.ts 2. Verify each prompt function (analyzeVariance, chatWithData, etc.) receives actual data objects from DB — not empty {} 3. In aiController.ts, confirm data is fetched from DB before calling AIService 4. Test: upload budget.csv → ask AI 'What is Engineering budget for Jan?' → AI must answer with the real value from uploaded file ACCEPTANCE: AI answer numbers match the CSV data you uploaded | backend/src/services/ai/prompts.ts backend/src/controllers/aiController.ts | 2–3 days | P0
3 | Verify real Groq/Gemini/Anthropic API calls — not simulated | 1. Add GROQ_API_KEY to .env 2. Start backend 3. POST to http://localhost:4000/api/ai/analyze-variance with real period data 4. Check backend logs for '[AI] Trying provider: groq' 5. Check response has 'provider: groq' badge 6. Disable GROQ_API_KEY → repeat → verify fallback to gemini 7. Disable both → verify fallback to anthropic ACCEPTANCE: 3 provider fallbacks confirmed with real API keys | backend/src/services/ai/AIService.ts | 1–2 days | P0
4 | Build PowerPoint (.pptx) Export | 1. Install pptx npm package in backend 2. Add generatePPTX() method to ReportService.ts 3. Each of the 10 board pack sections = 1 slide 4. Add route: GET /api/reports/:id/download?format=pptx 5. Add 'Export PPTX' button to /reports page ACCEPTANCE: Click Export PowerPoint → .pptx downloads → opens in PowerPoint with 10 slides and chart data | backend/src/services/ReportService.ts frontend/src/app/(dashboard)/reports/page.tsx | 3–4 days | P1
5 | Verify /forecasting page UI renders with real data | 1. Upload actuals CSV with 6+ months of data 2. Navigate to /forecasting 3. Verify: 3/6/12-month forecast line chart with shaded confidence band 4. Click 'Upside Scenario' → optimistic line appears 5. Click 'Downside Scenario' → pessimistic line appears 6. Verify assumptions text below chart lists growth rate used ACCEPTANCE: All 3 scenarios visible on chart with confidence bands | frontend/src/app/(dashboard)/forecasting/page.tsx | 1–2 days | P1
6 | Verify AI Insight Panel on every page | 1. Navigate to /dashboard → confirm AIInsightPanel shows 3 insights 2. Navigate to /variance → confirm panel shows 3 variance-relevant insights 3. Navigate to /budget → confirm panel shows 3 budget-relevant insights 4. Upload new data → confirm panel insights refresh ACCEPTANCE: Floating panel visible on all 6 main pages with context-appropriate insights | frontend/src/components/ai/AIInsightPanel.tsx | 1 day | P1
7 | Configure and test email sending (SMTP) | 1. Add to .env: SMTP_HOST, SMTP_PORT, SMTP_USER, SMTP_PASS (use Gmail app password) 2. Submit a budget for approval → check approver inbox 3. Set a scheduled report (daily) → check email arrives 4. Create variance >10% → check alert email received ACCEPTANCE: All 3 email types (approval, scheduled report, variance alert) received in inbox | backend/src/jobs/syncJobs.ts backend/src/services/EmailService.ts | 2–3 days | P1
8 | Live multi-user collaboration test | 1. Open Browser A as Admin, Browser B as Budget Owner 2. In Browser B: add comment on Engineering budget line → Browser A: verify comment visible 3. In Browser B: @mention Admin → Browser A: verify notification 4. In Browser B: submit budget for approval → Browser A: approve it 5. Verify status trail: Draft→Submitted→Under Review→Approved 6. In Browser A: go to Activity Log → verify all actions recorded ACCEPTANCE: All collaborative actions work between two live users | frontend/src/app/(dashboard)/budget/ backend/src/websocket/socketHandler.ts | 2 days | P1
9 | Build Variance Alert Threshold UI | 1. Add 'Alert Threshold %' input field to /variance page header 2. Save threshold to company settings in DB 3. In POST /api/variance/calculate: after computing variances, check if any exceed threshold 4. If exceeded: emit socket event + create in-app notification + trigger email alert ACCEPTANCE: Set 5% threshold → calculate variance with 15% item → alert email received + in-app toast shown | frontend/src/app/(dashboard)/variance/page.tsx backend/src/services/VarianceService.ts | 2–3 days | P2
10 | Test and verify Monthly Close checklist UI | 1. Go to /reports → find Monthly Close section 2. Verify interactive checklist with items: Actuals imported, Variances calculated, Board pack generated 3. Tick one item → verify state persists on page refresh 4. Click 'One-click Monthly Close' → verify all items auto-complete and status badge changes ACCEPTANCE: Checklist is interactive, state persists, one-click close works | frontend/src/app/(dashboard)/reports/page.tsx | 1 day | P2
11 | Verify Headcount Forecast chart with planned hires | 1. On /headcount page: click 'Add Planned Hire' 2. Enter: role=Senior Engineer, dept=Engineering, start=June 2025, salary=2400000 3. Verify 12-month chart shows headcount jump in June 4. Add 3 more planned hires → verify chart line updates ACCEPTANCE: Chart shows cumulative headcount line + salary cost projection with planned hires | frontend/src/app/(dashboard)/headcount/page.tsx | 1–2 days | P2
12 | Implement Attrition Risk Scoring | 1. In HeadcountService.ts: calculate risk score per dept based on: avg tenure < 1yr = HIGH, 1–3yr = MEDIUM, >3yr = LOW 2. Add risk badge to each dept card on /headcount page 3. Include attrition risk in AI headcount analysis prompt ACCEPTANCE: Each department card shows Low/Medium/High attrition risk with explanation | backend/src/services/HeadcountService.ts frontend/src/app/(dashboard)/headcount/page.tsx | 2 days | P2
13 | Verify WaterfallChart renders with real P&L data | 1. Upload p_and_l.csv 2. Navigate to /variance or /reports where WaterfallChart should appear 3. Verify bars show: Revenue → COGS → Gross Profit → OpEx items → EBITDA 4. Positive bars = green, negative = red ACCEPTANCE: WaterfallChart visible on at least one page with real P&L data | frontend/src/components/charts/WaterfallChart.tsx | 1–2 days | P2
14 | Verify CashFlowChart with uploaded cash flow data | 1. Upload cashflow.csv (12 months) 2. Navigate to /dashboard or /reports 3. Verify CashFlowChart renders with Operating/Investing/Financing/Net Cash bars 4. Hover shows exact ₹ values, negative bars in red ACCEPTANCE: CashFlowChart visible and accurate against cashflow.csv data | frontend/src/components/charts/CashFlowChart.tsx | 1 day | P2
15 | Performance test with 10,000+ row CSV | 1. Generate a CSV with 10,000 actuals rows (use Python script or spreadsheet) 2. Upload to /upload 3. Measure: processing time (should be <2 min), no timeout errors 4. After processing: go to /actuals → filter by department → verify all rows importable ACCEPTANCE: 10K rows process in <2 min, all rows in DB, no container crash | python_processor/processors/csv_processor.py backend/src/controllers/uploadController.ts | 1 day | P2
16 | KPI management from /settings page | 1. Go to /settings → find KPI section 2. Add KPI: name=CAC, unit=₹, target=100000, period=2024-03 3. Verify it appears in /dashboard 12-KPI grid 4. Edit target → verify grid updates ACCEPTANCE: KPIs are fully manageable from settings UI | frontend/src/app/(dashboard)/settings/page.tsx | 1 day | P3
17 | Test Google Sheets Connector (import) | 1. Add GOOGLE_CLIENT_ID + GOOGLE_SERVICE_ACCOUNT_KEY to .env 2. Go to /connectors → find Google Sheets card 3. Paste a public Google Sheet URL 4. Verify tabs are auto-detected, column headers read 5. Import data → verify rows in actuals table ACCEPTANCE: Data flows from Google Sheets into the app database | backend/src/controllers/connectorController.ts frontend/src/app/(dashboard)/connectors/page.tsx | 1–2 days | P3
18 | Bulk employee import via CSV | 1. On /headcount page: find 'Bulk Import' or 'Upload CSV' button 2. Upload headcount.csv (8 employees) 3. Verify all 8 employees appear in the roster without manual entry ACCEPTANCE: Bulk import works from upload page or headcount page | frontend/src/app/(dashboard)/headcount/page.tsx backend/src/controllers/headcountController.ts | 1 day | P3
19 | Mobile responsive testing | 1. Open Chrome DevTools → set viewport to 375px (iPhone) 2. Test each page: sidebar collapses, tables scroll horizontally, charts resize 3. Test file upload drag-drop on mobile 4. Test form inputs are usable on mobile keyboard ACCEPTANCE: All pages are usable on mobile without horizontal page scroll | frontend/src/components/layout/Sidebar.tsx frontend/src/app/(dashboard)/layout.tsx | 2–3 days | P3
20 | Redis cache validation | 1. Load /dashboard → note response time → load again within 5 min → should be faster 2. Upload new actuals → /dashboard should show updated data (cache invalidated) 3. Stop Redis: docker stop finbudget_redis → app should still work (degrade gracefully) ACCEPTANCE: Cache speeds up repeated reads, invalidates on write, app degrades gracefully without Redis | backend/src/config/redis.ts | 1 day | P3
21 | Cross-browser testing | 1. Test app in Chrome, Firefox, Safari, Edge 2. Check: all Recharts/Chart.js charts render, WebSocket connects, file upload works 3. Fix any rendering issues specific to a browser ACCEPTANCE: All core features work in all 4 browsers | frontend/ (all pages) | 1 day | P3
22 | Export report to Google Sheets | 1. From /reports: click 'Export to Google Sheets' 2. Authenticate with Google OAuth 3. Enter destination spreadsheet URL 4. Verify P&L data appears with correct columns and formatting ACCEPTANCE: Report data exported to a real Google Sheet | backend/src/services/ReportService.ts | 2–3 days | P3
23 | Production config — S3 storage + deployment docs | 1. Set STORAGE_MODE=s3 with real AWS credentials 2. Upload a file → verify in S3 bucket → download → confirm readable 3. Write README section: production deployment to Railway/Vercel/EC2 ACCEPTANCE: S3 upload/download works, deployment guide documented | backend/src/services/StorageService.ts README.md | 1–2 days | P3

## 🤖 AI Test Reality Check
🤖 AI Chat Test Reality Check — Simulated vs What Real Results Should Look Like
⚠️ All 15 AI chat tests in the test file were SIMULATED by Antigravity — not real API calls. Numbers may not match your actual uploaded CSV data.
# | Prompt Tested | Problem Found in Simulated Answer | What to Verify in Live Test | Red Flag
1 | Why did marketing spend go up in Q3? | Answer says '₹1.2L over budget' for Q3 Events. But sample budget.csv has Marketing Events at ₹2.0L–₹10.0L/month — the simulated variance doesn't match the sample data structure. | Upload budget.csv + actuals_2024_03.csv → ask this question → verify the AI quotes numbers that MATCH the actual rows in those files. | Numbers don't match sample CSV
2 | What is our current burn rate and runway? | Answer says 'burn rate ₹43L/month, runway 18 months'. The sample budget.csv total monthly expense is much lower. Cash reserve data was never uploaded — runway calculation is hallucinated. | Upload cashflow.csv → ask burn rate → AI must calculate from Operating Activities column in that file. Answer should match cashflow.csv row for the latest period. | Hallucinated — no cash data uploaded
3 | Which departments are over budget this month? | Answer says 'Engineering UNFAV by ₹45K'. But no actuals were uploaded before this simulated test — the AI had no actual data to compare against the budget. | Upload budget.csv + actuals_2024_03.csv → POST /api/variance/calculate → ask this question → AI must list exact departments from the variance table. | Variance not calculated — no live data
4 | Generate an executive summary for the board | Answer says 'revenue ₹1.12 Cr, net income ₹22L'. These exact numbers appear nowhere in the sample data provided (budget.csv revenues are ₹80L–₹1.2Cr depending on month). Could be coincidence or hallucination. | With real data uploaded: verify AI summary cites numbers that match actuals and P&L uploaded. Check specific ₹ amounts match the CSV rows. | Revenue figures may be hallucinated
5 | What would happen if we cut 10% from all operating expenses? | Answer gives precise 'saves ₹4.5L/month'. This requires the AI to know current total OpEx — which was never passed from the DB into the prompt in any confirmed test. | Verify aiController.ts fetches total actuals from DB before calling chatWithData(). The ₹ number in the answer should match SUM of actuals for the uploaded period. | OpEx total may not be from DB
6 | Are we on track to hit annual revenue target? | Answer says 'MRR ₹95L, ARR ₹11.4Cr'. The sample budget.csv Product Revenue is ₹80L–₹1.2Cr/month — an ARR of ₹11.4Cr is plausible but needs to be verified against actual DB values. | Verify AI computes YTD actuals revenue / months elapsed × 12 = projected ARR, compared against budget.totalRevenue from the BudgetPlan record in DB. | Formula basis not confirmed
7 | Which KPIs are most at risk? | Answer mentions 'CAC ₹1.25L' and 'Gross Margin 65%'. Neither value exists in kpis.csv sample data (KPI sample has generic Metric Name/Value format). These appear to be hallucinated. | Upload kpis.csv → verify AI answer quotes the exact Metric Name and Value columns from that file. CAC should only be mentioned if a KPI row named 'CAC' exists in the uploaded file. | KPI values hallucinated from thin air
8 | How does headcount cost compare to budget? | Answer gives exact per-dept salary totals that happen to match the headcount.csv data — but the simulated test ran before data was uploaded, so this is coincidence or the AI was primed. | Upload headcount.csv → POST /api/headcount/import → ask question → verify AI quotes exactly the salaries from headcount.csv rows (e.g., EMP001 Priya Sharma ₹2.8L salary). | May be primed — not from live DB
9 | What is our gross margin this month? | Answer gives '65.1% gross margin' calculated as (11.2M - 3.9M) / 11.2M. But p_and_l.csv was listed in the test file but its actual sample data was not fully shown — unclear if these numbers match. | Upload p_and_l.csv → ask gross margin → verify AI uses Revenue and COGS columns from that exact file. The % must match: (Revenue - COGS) / Revenue for the most recent period row. | Calculation basis unverified
10 | Forecast revenue for next 3 months | Answer gives '₹1.14Cr, ₹1.18Cr, ₹1.24Cr' based on '6 months of P&L data'. But only 6 rows of P&L were in the sample — and these are budget rows, not actuals. | Verify forecast_engine.py is called with real historical actuals (not budget). Forecasts should be based on Actuals table data, not BudgetLine data. | Forecast may use wrong data source
11 | Why is Engineering variance unfavorable? | Answer cites 'EMP006 (DevOps) onboarding two weeks early' which is exactly in the headcount.csv sample. This is a good sign — but it needs to be confirmed the AI actually read from DB, not from its training on the sample data. | After uploading headcount.csv and uploading actuals, ask this question → AI must name the specific employee AND account code (5001 or 5002) from the uploaded data. | May be coincidence — verify with live data
12 | Top 3 cost reduction opportunities? | Answer says 'switch to reserved instances, pause events, optimize CAC'. Generic CFO advice — not necessarily grounded in the company's specific cost structure from uploaded files. | Verify AI references specific Account Codes from chart_of_accounts.csv when making recommendations (e.g., 'Account 5002 Cloud Infra shows 30% over budget'). | Generic advice — not data-specific
13 | Is our cash flow healthy? | Answer says '₹58L from Operating Activities in March'. cashflow.csv sample has 12 months of data — this number needs to be verified against the actual row in the file. | Upload cashflow.csv → ask cash flow health → verify AI cites the correct period's Operating Activities amount from the file. | Amount needs CSV verification
14 | What changed most between Feb and March? | Answer says 'Revenue jumped 5.6% (+₹6L)'. This requires two periods of actuals. Only one actuals file was uploaded (actuals_2024_03.csv — March only). Feb comparison requires actuals_jan_2025.csv or a Feb file. | Upload BOTH a Feb actuals file AND a March actuals file → then ask this question → AI must compare the two periods. Without both periods uploaded, the AI has no basis for period-over-period analysis. | Missing Feb actuals file for comparison
15 | Which employees are in salary-overbudget depts? | Answer names 'Deepa Mehta (EMP006)' who is exactly in headcount.csv. This is very specific — confirms the AI either read from DB (good) or memorised the sample data (concerning). | Upload headcount.csv → calculate variances → ask this question → AI must name the employee AND their account code deviation. Then change a salary in the DB and re-ask — answer must change accordingly. | Verify AI reads DB, not memorised data

## 📭 Not Tested
📭 Features in Spec NOT in Any Test Case — Zero Coverage
# | Feature (from original spec) | Why It Matters | How to Test | Priority
1 | WaterfallChart component | P&L bridge analysis is a core CFO tool — shows how revenue walks down to net income | Upload p_and_l.csv → navigate to a page that uses WaterfallChart → verify bars show Revenue→COGS→GP→OpEx→EBITDA | P1
2 | CashFlowChart component | Cash flow visualization is required for board pack and dashboard | Upload cashflow.csv → find CashFlowChart on /dashboard or /reports → verify 4-column bar chart (Operating, Investing, Financing, Net) | P1
3 | AIInsightPanel on every page | Spec says floating panel with top 3 insights visible on ALL dashboard pages | Navigate to each of 6 dashboard pages → confirm AIInsightPanel component visible → insights are page-context-relevant | P1
4 | Forecasting page UI /forecasting | Spec has a full page with confidence interval chart, scenario toggles, assumptions text | Go to /forecasting → verify chart with shaded confidence bands → toggle Upside/Downside scenarios | P1
5 | PowerPoint .pptx export | Spec explicitly requires 'Export as PowerPoint (pptx)' from board report generator | Click Export PPTX → file downloads → opens in PowerPoint → 10 slides with content | P1
6 | Revenue vs Budget chart drill-down | Spec says 'click to drill down' on chart — no test for drill-down interactivity | Click a bar in the Revenue vs Budget chart → verify drill-down to department/category level | P2
7 | Expense donut chart — click to filter | Spec says clicking a donut segment filters the table below | Click a segment in the Expense Breakdown donut → verify table below filters to that category | P2
8 | Headcount forecast with planned hire timeline | Spec requires adding planned hires month-by-month and seeing cumulative chart update | Add a planned hire → verify 12-month headcount chart updates with the new hire in the correct month | P2
9 | Attrition risk scoring per department | Spec requires attrition risk score — no test case for this at all | On /headcount: verify each dept card shows Low/Medium/High attrition risk indicator | P2
10 | Cost-to-hire tracking | Spec requires cost-to-hire tracking per open role | On /headcount: verify open role cards show estimated cost-to-hire (recruiter cost + salary ramp) | P2
11 | Landing page (/) | The landing page (hero section, features, CTA) — not tested | Navigate to http://localhost:3000 (not logged in) → verify landing page renders with app description and 'Get Started' CTA | P3
12 | Budget comments + @mention notifications | Multi-user commenting system — zero live test coverage | Two-browser test: add comment with @mention → second user sees notification → notification links to correct budget line | P1
13 | Budget approval email notifications | Spec requires email on approval/rejection — only static check done | Submit budget → approver approves → submitter gets email → verify email content includes budget name and approver name | P1
14 | Activity log (who changed what) | Audit trail is critical for finance compliance — not live-tested | Make 5 changes (edit budget, approve, lock, add employee, calculate variance) → go to Activity Log → all 5 show with timestamp, user, action | P2
15 | Currency auto-detection ₹ vs $ | Spec requires auto-detecting currency from uploaded data | Upload a CSV with USD amounts ($) → verify dashboard shows $ → upload a ₹ CSV → verify dashboard switches to ₹ | P2
16 | Google Sheets export (not just import) | Spec requires exporting reports TO Google Sheets | From /reports: click Export to Google Sheets → authenticate → verify data appears in a Google Sheet | P3
17 | Bulk employee import via CSV | API endpoint exists but no UI button confirmed | On /headcount: find Bulk Import button → upload headcount.csv → all 8 employees appear without manual entry | P3
18 | Settings page: AI provider key management | Spec requires configuring API keys from UI, not just .env | Go to /settings → AI providers section → enter Groq API key → test connection → verify green Connected badge | P2
19 | Settings page: user invite + deactivate | Admin user management from UI, not just via DB | Go to /settings → Users → invite by email → set role → deactivate → verify cannot login | P2
20 | KPI CRUD from settings | Settings should allow adding/editing KPIs | Go to /settings → KPI section → add new KPI → verify it appears on /dashboard | P2
21 | P&L data in p_and_l.csv — verify AI reads it | p_and_l.csv exists but AI gross margin test may not have used it | Upload p_and_l.csv → ask 'what is our gross margin' → verify AI quotes exact Revenue and COGS numbers from that file | P1

## 📅 Sprint Plan
📅 Recommended Sprint Plan — From Test Results to Production-Ready
── SPRINT 0 (Pre-work) ~1 day — Environment Setup ──
→ | Set up API keys: GROQ_API_KEY, GEMINI_API_KEY, ANTHROPIC_API_KEY in .env | P0 — Blocker
→ | Set up SMTP credentials (Gmail app password) | P0 — Blocker
→ | Run: docker-compose up --build | P0 — Blocker
→ | Run: npx prisma migrate dev | P0 — Blocker
→ | Confirm: http://localhost:3000 loads | P0 — Blocker
→ | Confirm: curl localhost:4000/api/health → 200 | P0 — Blocker
→ | Confirm: curl localhost:5001/health → 200 | P0 — Blocker
── SPRINT 1 (Week 1) ~5 days — Critical: Live Testing + AI Grounding ──
→ | Manually re-run all 104 test cases on live running app | P0–P1 Critical
→ | Upload all 7 CSV files and verify data in DB | P0–P1 Critical
→ | Verify AI calls hit real Groq API (not simulated) | P0–P1 Critical
→ | Verify AI prompts.ts injects real DB data into context | P0–P1 Critical
→ | Re-run all 15 AI prompts with real data — verify numbers match CSV | P0–P1 Critical
→ | Fix any test failures found (expected: 10–20% of tests will fail on live run) | P0–P1 Critical
→ | Fix: PowerPoint .pptx export | P0–P1 Critical
── SPRINT 2 (Week 2) ~5 days — High Priority Features + Email ──
→ | Configure SMTP — test all 3 email types (approval, scheduled, alert) | P1 High
→ | Verify /forecasting page UI with confidence band chart + scenario toggles | P1 High
→ | Verify AIInsightPanel on every dashboard page | P1 High
→ | Live multi-user collaboration test (2 browsers) | P1 High
→ | Build Variance Alert Threshold UI | P1 High
→ | Fix: Waterfall chart + Cash Flow chart with real uploaded data | P1 High
── SPRINT 3 (Week 3) ~5 days — Medium Priority Features ──
→ | Monthly Close checklist interactive UI | P2 Medium
→ | Headcount forecast chart with planned hires | P2 Medium
→ | Attrition risk scoring per department | P2 Medium
→ | KPI CRUD from settings page | P2 Medium
→ | Currency auto-detection ₹/$ from uploaded data | P2 Medium
→ | Activity log + user management from settings | P2 Medium
→ | Performance test: 10,000-row CSV upload | P2 Medium
── SPRINT 4 (Week 4) ~3 days — Low Priority + Production Readiness ──
→ | Google Sheets connector (import + export) | P3 Low + Launch
→ | Bulk employee import via CSV | P3 Low + Launch
→ | Mobile responsive testing + fixes | P3 Low + Launch
→ | Redis cache validation | P3 Low + Launch
→ | Cross-browser testing (Chrome/Firefox/Safari/Edge) | P3 Low + Launch
→ | S3 storage configuration + production deployment docs | P3 Low + Launch
→ | Final: all 104 + new test cases marked by human tester | P3 Low + Launch